## Sheet1
ACES OF GRACE DEBIT MEMO
# | TASK DETAILS | MODULE PARTS | PROGRESS | STATUS | DATE START | DATE ACCOMPLISH | PROCESS | Remarks
1 | Create Report that summarize total debit of Branches with date range and Supervisor as well | REPORTS | 100% | COMPLETED | 2018-06-08 | 2018-06-12 | User have selection what type of report he/she wanted to view(Branch and Supervisor)
2 | Approve incrementation notifcation on regular user account | My Request Form | 100% | COMPLETED | 2018-06-08 | 2018-06-08 | User need to POST the approve DM to enable print and flag the IsPosted field | Requirement to enable posting is the flag IsComplete should be true.
3 | Create Debit Memo Item Maintenance | Maintenance | 100% | COMPLETED | 2018-06-11 | 2018-06-13
5 | Create Personnel Maintenance | Maintenance | 100% | COMPLETED | 2018-06-13 | 2018-06-14
6 | Create Dispatch Module | Dispatch Form | 100% | COMPLETED | 2018-06-18 | 2018-06-18
7 | Configure and setup server | Hardware Requirement | 100% | COMPLETED | 2018-07-05 | 2018-07-05 |  | This will server temporary server / specs is Workstation CPU | STATUS
8 | Deployment and Implementation of Debit Memo | Setup | 100% | COMPLETED | 2018-07-06 | 2018-07-06 | Need to start to be able to identify any concern and bugs. | Start of Debit Memo System | ON PROCESS
9 | Additional Voucher Module for Ma'am Anna | Voucher | 50% | ON PROCESS | 2018-07-06 |  | Ms. Anna need to encode details for payment, requirement selection of Supplier to be paid. | It would be possible to have Supplier Maintenance | NOT YET STARED
10 | [8 empty] | PENDING
11 | [8 empty] | COMPLETED
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Sheet2
Summary Detail - All | repDebitMemoTotalSummary_Details | DMS
Summary List - All | repDebitMemoTotalSummary_List | DMS
Supervisor Summary Details | repDebitMemoTotalSummary_Details_Supervisor | DMS
Supervisor Summary Lists | repDebitMemoTotalSummary_List_Supervisor | DMS